## Daily Work
Eckard Bank & Trust Project Daily Work
Date | Work Completed | Roadblocks | Resolutions
2025-08-26 | Created Workflow for Derek and Daily Work journal. Determined to convert current code from C++ to Visual BASIC. | Currently learning Visual BASIC and am missing knowledge | Plan to convert the code as I learn VB in the next two months.
2025-08-28 | Began work on creating Visual Studio solution roadmap with each needed separate project within the solution. Created the UI's for the Main Menu and New Account files. | Unsure how to add additional files and projects into a solution. | Researched online resourses and followed a step by step guide.
2025-09-02 | Created all UI's and dialog boxes. Started on Planning charts for each UI. | Nothing of concern
2025-09-04 | Finished Planning charts. Documented and began coding NewAcct UI. Created click event sub in AcctSummary.vb that shows and hides the account number. | Creating additional forms for dialog boxes seemed cumbersome. | Researched a cleaner solution and learned about 'MessageBox.Show() and the DialogResult data type.
2025-09-09 | Created detailed project tracker. Created planning chart and UI for IncorrectDataDia.vb. Condensed multiple event procedures. | Difficulties with assigning multiple controls for a ToolTip. | Create a Control variable and use DirectCast() to allow multiple controls to use the toolTip.
2025-09-11 | Created Application workflow. Commented out code sections. Listed out needed variables and constants. Started on basic navigation between Uis. | Nothing of concern
2025-09-16 | Added project tracker to Planner app in Teams. Finished basic navigation for testing. | Navigating back to an existing form without creting a new instance. | Will need to learn process at a later time. Created new instances for navigation testing.
2025-09-18 | Used a portion of the program code for a class assignment, which wrote out some of the needed code. Revised and transferred that code to the main project. Referenced modules to UI files to begin creating functions. | Once modules were referenced to the Uis, it caused the Anti-Virus to block the running on the app. | Consulted with Adam S and was advised to get Shawn to Whitelist my Dev folder to allow access.
2025-09-23 | Worked on the frmMoveMoney UI and logic. Created the deposit and withdraw functions and the overdraft check. | Nothing of concern
2025-09-25 | Worked on creating flowcharts for the EBaT_UI form event procedures | Nothing of concern
2025-09-30 | Completed UI flowcharts. | Lack of knowledge to code sections | Learning additional chapters.
2025-10-02 | Created testing functions for creating StreamWriter and StreamReader variables to create new accounts, edit existing, and "Export" account details. | Goal is to store user data using a SQL database. Have not learned about SQL at this time. | Recently learned about using .txt files and using that knowledge to create DataAccess functions to test Logic functions.
2025-10-07 | Worked on creating validation functions for when all fields are not filled on the frmNewAcct UI and displaying the data on the IncorrectDataDia UI. | Struggling to connect info from frmNewAcct and IncorrectDataDia. | Researched how to send over data by using a public property.
2025-10-09 | Reworked the models.vb project to have two class files(UserData and CustAcct) and coded each class. Also documented each project file's current functions and subs(working documents). Modifying password requirements colored labels to display tooltips for each. Began connecting class objects to pass between UIs. | Nothing of concern
2025-10-14 | Created test class objects for for passing between UIs. Converted logic and validation functions from logic project to methods within the classes. Set up the frmAcctSummary UI to display test class object on load. | Nothing of concern
2025-10-21 | Decided to scrap the "IncorrectDataDia.vb" form to and replace with generic message boxes. Plan to repurpose form to be a summary dialog form that shows what information was updated in the "CustEdit" form. Began work on making that transition. | Nothing of concern
2025-10-23 | Continued work on transitioning dialog forms and updating flowchart and related planning charts. | Nothing of concern
2025-10-24 | Created logic for validation of fields when NewAcct form is submitted, including visual validation of testing "Unique Username". Set as True to progress app. | On Testing, the username visual validation was not displaying as "Valid" when typed. Should have been true in all occurrences. | Will research at a later time.
2025-10-28 | Created functions that looked at the updated customer fields and displays the data in the EditConfirmDia form | Nothing of concern
2025-10-30 | Refined EditConfirmDia form to account for different kinds of input or lack of input. Coded validation steps for frmCustEdit submit sub. | Nothing of concern
2025-11-06 | Reviewed chapter text regarding SQL Server Databases | Nothing of concern
2025-11-11 | Scraped SQL Database storage and have opted to store data in a master .txt file. Cleaned up code for better memory usage by storing data in simple variables instead of pulling data from controls like Textboxes. | Nothing of concern
2025-11-13 | Began coding functions to use .txt files as storage. Used DataAccess functions to code log in validation functions for user data. | Nothing of concern
2025-11-18 | Corrected issue that caused the Submit button to not process on CustEdit form. Ran into issues with master data file updating. Researching. | Ran into issues with master data file updating when using CustEdit form. | Researching.
2025-11-20 | Worked on getting master data file to update when submitting change. Made multiple edits and rewrites but still not getting change. | Same issues. | Reached out to CVCC instructor (Fred Richard) for assistance in looking over my code.
2025-12-02 | Determined cause of master file not updating and re-coded the function to work properly. Coded function to export customer data. Added visual in NewAcct UI that displays if entered username is unique or not. | Nothing of concern
2025-12-04 | Program fully works in current state as intended. Beginning to debug and test. As well as working on improving the UIs visually. Created a check thath looks for the "RawData.txt" file when the program opens and if not found, creates a file with sample data. Sent program out to start UAT testing. | Nothing of concern
2025-12-09 | Reviewed UAT feedback and made corrections that were called out. A side affect of making corrections was other code not working. Rewrote needed code . | Nothing of concern
2025-12-11 | Created EBaT_Audit project and Audit.vb class and made methods to track all important user movement within the app. Began reviewing each UI for various housekeeping fixes and polish, such as consistent terminology, title bars, and form size. | Nothing of concern
2025-12-12 | Finished visual housekeeping/polish of all UIs. Included an icon to forms. Reviewed MessageBoxes for consistence. Fixed logic error that would not update user data if they removed an address 2(apartment) data field. Started on cleaning up each code file, such as excessive spaces, unneeded sections, and missed documentation. | Nothing of concern
2025-12-15 | Completed review of all code. Created agenda for Demostration. | Nothing of concern

## Check-Off List
Housekeeping Check-Off List
Project Files | Code Clean-up | Accept | Cancel | Min btn | Max btn | Access Keys | Title Bar | Terminology | Form Size | Ctrl Spacing
MainMenu.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
NewAcct.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
LogIn.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CustMenu.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
CustEdit.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
EditConfirmDialog.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
MoveMoney.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
AcctSummary.vb | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Logic.vb | FALSE
Validation.vb | FALSE
DataAccess.vb | FALSE
CustData.vb | FALSE
CustAcct.vb | FALSE
Audit.vb | FALSE